## Product Backlog
Product Backlog for CA2
Priority | Item | Effort Required (man hours)
1 | Create ETL Pipeline to Connect SQL Database and Python | 1 | 10
2 | Aggregate sensor_data and driver_data based on booking id or driver id and the aggregated data to safety_labels | 2 | 5
3 | Perform PCA | 3 | 150
4 | Perform Feature Importance | 3 | 127
5 | Perform high-dimensional outlier detection using models such as Isolation Forest, LocalOutlierFactor and SVM and determine best model | 5
6 | Handle inbalanced data using Random Under Sampling, Random Over Sampling, and SMOTE and determine best model | 4 | 360
7 | Select best model and the number of principal components for best result | 4 | 20
8 | Perform grid search on selected model | 12 | 55
9 | Add GUI Interface to make predictions | 4
10 | Project Report | 6 | 15
11 | Bi-Weekly Scrum Reports + User Story | 3 | 21
| Total = | 47 | 763